## Epic
Build an Azure Landing Zone
Description: As an organization, one of the first steps to cloud adoption is to build a Landing Zone. The term landing zone refers to an environment that's been provisioned and prepared to host workloads in a cloud environment. More information can be found here: https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/considerations/
User Stories
1.) As a cloud enablement team, we need to understand the fundamental concepts of Azure.
2.) As a cloud enablement team, we need to define corporate Roles and Responsbilities as well as define a governance stragegy for our core enabled services
3.) As a cloud enablement team, we need to define and enforce security controls to match Corporate complaince requirements
4.) As a Cloud enablement team, we need to define resource naming and tagging strategies for corporate resources
5.) As a cloud enablement team, we need to extend our corporate network into the cloud
6.) As a cloud enablement team, we need to define compute requirements and deploy shared services into the cloud
7.) As a cloud enablement team, we need to define and deploy storage requirements into the cloud
8.) As a cloud enablement team, we need to implement a monitoring strategy to analyze, audit and alert corporate cloud resources.

## Fundamentals
Story: As a cloud enablement team, we need to understand fundamental concepts of Azure
Acceptance Criteria: Cloud Enablement team should be able to certify at the Az-900 (Azure Fundamentals) Level - https://docs.microsoft.com/en-us/learn/certifications/exams/az-900
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Review Role Based Access Control in Azure | Required for Understanding governance methodologies |  |  |  |  | https://docs.microsoft.com/en-us/azure/role-based-access-control/overview
2 | Review Azure Policies & Initiatives | Required for understanding governance methodologies |  |  |  |  | https://docs.microsoft.com/en-us/azure/governance/policy/overview
3 | Review Basic Cloud Concepts | Required to understand foundational cloud concepts |  |  |  |  | https://docs.microsoft.com/en-us/learn/modules/principles-cloud-computing/
4 | Review IaaS/PaaS/SaaS/Serverless concepts | Required to understand foundational cloud concepts |  |  |  |  | https://azure.microsoft.com/en-us/overview/what-is-iaas/
5 | Review Region & Availability Zone Concepts | Required for understanding core Architectural components |  |  |  |  | https://azure.microsoft.com/en-us/global-infrastructure/regions/ https://docs.microsoft.com/en-us/azure/availability-zones/az-overview
6 | Review Azure Resource Manager | Required for understanding core Architectural components |  |  |  |  | https://docs.microsoft.com/en-us/azure/azure-resource-manager/management/overview
7 | Review azure services | Required for understanding core Products available in Azure | Core Services include: Compute, Databases,Containers, Virtual Networks, Load Balancers, Storage, CDN, Web apps, Functions, Messaging Services, Azure AD and Migration Services |  |  |  | https://azure.microsoft.com/en-us/services/
8 | Review Azure Management Tools | Required for understanding platform management capabilities | Management tools include: Azure Portal, Powershell, CLI, Cloud Shell, Azure Advisor |  |  |  | https://azure.microsoft.com/en-us/features/azure-portal/ https://docs.microsoft.com/en-us/cli/azure/what-is-azure-cli?view=azure-cli-latest https://docs.microsoft.com/en-us/powershell/azure/new-azureps-module-az?view=azps-3.7.0 https://docs.microsoft.com/en-us/azure/cloud-shell/overview
9 | Review Azure AD | Required for understanding core Identity services |  |  |  |  | https://azure.microsoft.com/en-us/resources/videos/what-is-active-directory/
10 | Review Network connectivity services | Required for understanding network services in Azure |  |  |  |  | https://docs.microsoft.com/en-us/azure/networking/networking-overview
11 | Review Network Security services | Required for understanding security services in Azure |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/network-overview
12 | Review azure security tools | Required for understanding security tooling in Azure |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/services-technologies
13 | Review Azure Monitor Service | Required for understanding options for monitoring workloads in Azure |  |  |  |  | https://docs.microsoft.com/en-us/azure/azure-monitor/overview
14 | Review service trust portal | Required for understanding Privacy,Complians and Data Protection standards in Azure |  |  |  |  | https://servicetrust.microsoft.com/
15 | Review Azure Cost estimation and management options | Required for understanding pricing and cost management in Azure |  |  |  |  | https://docs.microsoft.com/en-us/azure/cost-management-billing/cost-management-billing-overview
16 | Review platform support options | Required for understanding support options in Azure |  |  |  |  | https://azure.microsoft.com/en-us/support/plans/
17 | Review Service Level Agreement information | Required for understanding SLA for services consumed in Azure |  |  |  |  | https://azure.microsoft.com/en-us/support/legal/sla/
18 | Review roadmap site | Required for keeping track of when service offerings will be made generally available in Azure |  |  |  |  | https://azure.microsoft.com/en-us/updates/

## Roles&Responsibilities
Story: As a cloud enablement team, we need to define corporate Roles and Responsbilities as well as define a governance stragegy for our core enabled services
Acceptance Criteria: Cloud Eanblement team should have a clearly defined RACI document that defines responsibility alignment for project delivery - (Sample can be found here: https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/organize/raci-alignment)
TASKS
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Define an Executive Sponsor to support project initiative | An Executive sponsor is a high level individual who has the ability to set priority within the company and drive collaboration across business units
2 | Define team Alignment for compute platform | Define the following: Owners/ Contributors/Readers
3 | Define team Alignment for networking platform | Define the following: Owners/ Contributors/Readers
4 | Define team Alignment for identity platform | Define the following: Owners/ Contributors/Readers
5 | Define team Alignment for storage platform | Define the following: Owners/ Contributors/Readers
6 | Define Team Alignment for serverless platform | Define the following: Owners/ Contributors/Readers
7 | Define team Alignment for security platform | Define the following: Owners/ Contributors/Readers
8 | Define corporate policy | Define business processes and technology required for platform adoption |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/govern/corporate-policy
9 | Define Hierarchy for resource organization | build a governance topology for organizing cloud resources |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/govern/guides/complex/#resource-organization
10 | Map corporate policy to Azure policy definitions | Required to ensure and enforce policy adherance within platform |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/govern/guides/complex/#identify-policy-definitions
11 | Map team alignments to RBAC roles | Required to ensure required access to Azure resources based on alignment |  |  |  |  | https://docs.microsoft.com/en-us/azure/role-based-access-control/built-in-roles

## Security
Story: As a cloud enablement team, we need to define and enforce security controls to match Corporate complaince requirements
Acceptance Criteria: Review & Deploy azure services to audit, enforce and enable security controls to meet corporate compliance standards
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Define business risk and build a security baseline for our cloud adoption plan | [5 empty] | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/govern/security-baseline/template
2 | Define IAM security controls | Document security controls required for Identity and Access services, this may or may or may not overlap with existing compliance certification controls |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/identity-management-best-practices?toc=/azure/cloud-adoption-framework/toc.json&bc=/azure/cloud-adoption-framework/_bread/toc.json
3 | Define network security controls | Document security controls required for Network services, this may or may or may not overlap with existing compliance certification controls |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/network-overview
4 | Define Data security controls | Document security controls required for Data services, this may or may or may not overlap with existing compliance certification controls |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/encryption-overview
5 | Define Virtual Machine Security Controls | Document security controls required for Compute services, this may or may or may not overlap with existing compliance certification controls |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/virtual-machines-overview
6 | Define PaaS services Controls | Document security controls required for Managed services, this may or may or may not overlap with existing compliance certification controls |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/service-fabric-best-practices
7 | Review complaince certifications based on corporate industry requirements | Document complains certifications required for certification of workloads in Azure. Begin the process of certifying services through internal processes |  |  |  |  | https://azure.microsoft.com/en-us/overview/trusted-cloud/compliance/
8 | Enable unified infrastructure security management solution and map required compliance controls | Using built-in and custom policies, map corporate security controls to security center for auditing and remediation of infrastructure |  |  |  |  | https://docs.microsoft.com/en-us/azure/security-center/security-center-intro
9 | Enable platform based thread hunting service for SecOps monitoring and investigation | leveraging platform based analytics and machine learning, gain additional insights from built in platform logging |  |  |  |  | https://docs.microsoft.com/en-us/azure-advanced-threat-protection/what-is-atp
10 | Enable cloud native SEIM and security orchestration tooling for advanced analytics, investigation and automated incident mitigation | Required to take advantage of cloud native tooling for security orchestration and threat investigation without having to build additional footprint onprem. |  |  |  |  | https://docs.microsoft.com/en-us/azure/sentinel/overview

## Naming&Tagging
Story: As a Cloud enablement team, we need to define resource naming and tagging strategies for corporate resources
Acceptance Criteria: create a naming and tagging matrix that defines the strategic labeling of resources defined in Azure - (Example Naming and Tagging Tracking template can be found here: https://archcenter.blob.core.windows.net/cdn/fusion/readiness/CAF%20Readiness%20Naming%20and%20Tagging%20tracking%20template.xlsx)
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Review rules and restrictions for naming resources | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-resource-manager/management/resource-name-rules
2 | Determine naming scope based desired business component | Compenent can be any of the following: Business Unit /Subscription Type/ Application/ Environment/Region |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/azure-best-practices/naming-and-tagging#recommended-naming-components
3 | Create standard naming prefix based on resource | Naming prefix required for enabling consistency in reporting and provisioning of resources |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/azure-best-practices/naming-and-tagging#recommended-resource-type-prefixes
4 | Create resource tagging matrix based on resource | Tagging matrix required for enabling consistency in reporting, provisioning, billing and other abilities to manage and maintain cloud infrastructure |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/azure-best-practices/naming-and-tagging#metadata-tags
5 | Define policies for enforcing tagging governance | Required to ensure all assets in cloud are properly tagged and accounted for |  |  |  |  | https://docs.microsoft.com/en-us/azure/governance/policy/tutorials/govern-tags
6 | Define scoping levels for policy enforcement within organization | Ensures resources and services that are deployed at different layers within the governance topology get the appropriate tagging and naming policies applied |  |  |  |  | https://docs.microsoft.com/en-us/azure/governance/policy/overview

## Networking
Story: As a cloud enablement team, we need to extend our corporate network into the cloud
Acceptance Criteria: Implement a secure hybrid network architecture
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Review and assign appropriate region pair for initiative | Identifying appropriate region pairs ensures highest RTO and RPO objectives are met for DR scenarios |  |  |  |  | https://docs.microsoft.com/en-us/azure/best-practices-availability-paired-regions
2 | Asign a non-overlapping CIDR block for private network connectivity | This will be the master block from which you carve out and assign all virtual network CIDR within your cloud infrastructure. Recommended to use between a /20 - /16 based on scale
3 | Deploy Virtual network in pre-determined required regions | Reguired to configure regional datacenter footprint on cloud platform. |  |  |  |  | https://docs.microsoft.com/en-us/azure/virtual-network/virtual-network-vnet-plan-design-arm?toc=https://docs.microsoft.com/azure/cloud-adoption-framework/toc.json&bc=https://docs.microsoft.com/azure/cloud-adoption-framework/_bread/toc.json#regions
4 | Segment Virtual network into delegated subnet spaces | Recommended to reserve at least 4 /27 subnets at the top of your Vnet range. This will enable you to delegate managed service such as: Bastion, App Gateway and others |  |  |  |  | https://docs.microsoft.com/en-us/azure/virtual-network/subnet-delegation-overview
5 | Determine Gateway connectivity requiremens back on premise | Required in order to select appropriate connectivity option to match Scalability and security requirements |  |  |  |  | https://docs.microsoft.com/en-us/azure/architecture/reference-architectures/hybrid-networking/vpn#scalability-considerations https://docs.microsoft.com/en-us/azure/architecture/reference-architectures/hybrid-networking/expressroute#scalability-considerations
6 | Implement Gateway connectivity to on premise | [5 empty] | https://docs.microsoft.com/en-us/azure/vpn-gateway/vpn-gateway-howto-site-to-site-resource-manager-portal https://docs.microsoft.com/en-us/azure/expressroute/expressroute-howto-circuit-portal-resource-manager
7 | Determin Routing strategy for network traffic | Required in order to manage movement of traffice within Hybrid network infrastructure |  |  |  |  | https://docs.microsoft.com/en-us/azure/virtual-network/virtual-networks-udr-overview
8 | Determine network security security requirements for ingress/egress packet flows | Required for segmentation and for securing services to private network. |  |  |  |  | https://docs.microsoft.com/en-us/azure/security/fundamentals/network-best-practices#secure-your-critical-azure-service-resources-to-only-your-virtual-networks
9 | Implement network routing rules | [5 empty] | https://docs.microsoft.com/en-us/azure/virtual-network/tutorial-create-route-table-portal#create-a-route-table
10 | Implement network security groups/ firewalls/NVAs | [5 empty] | https://azure.microsoft.com/en-us/blog/best-practices-to-consider-before-deploying-a-network-virtual-appliance/ https://docs.microsoft.com/en-us/azure/virtual-network/tutorial-restrict-network-access-to-resources
11 | Plan and configure Name resolution for virtual network | Requires in order to enable DNS within hybrid architecture |  |  |  |  | https://docs.microsoft.com/en-us/azure/virtual-network/virtual-networks-name-resolution-for-vms-and-role-instances

## Compute
Story: As a cloud enablement team, we need to define compute requirements and deploy shared services into the cloud
Acceptance Criteria: Enabled a centralized environment in which all commonly used services reside
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Delegate a shares services subnet, deploy shared compute resources | Resources can include: Active Directory, Time Server, Dns Servers, etc. Subnet typically resides in Gateway enabled virtual network |  |  |  |  | https://docs.microsoft.com/en-us/windows-server/identity/ad-ds/deploy/virtual-dc/adds-on-azure-vm
2 | Enable policies to restrict creation of compute resources outside of scope | [5 empty] | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/considerations/compute-options#establish-controls-for-compute-services
3 | Delegate a Firewall subnet, deploy NVA or Azure firewall to controll the flow of traffic to shared services and between virtual networks | Required for filtering and auditing traffic between network |  |  |  |  | https://docs.microsoft.com/en-us/azure/firewall/overview https://azure.microsoft.com/en-us/blog/azure-firewall-and-network-virtual-appliances/
4 | Configure Availability sets/Availability zones where appropriate | Required for enhanced resiliency |  |  |  |  | https://docs.microsoft.com/en-us/azure/virtual-machines/windows/manage-availability
5 | Deploy load balancers for Availability set/zone configured vms | required for enhanced resiliency |  |  |  |  | https://docs.microsoft.com/en-us/azure/load-balancer/tutorial-load-balancer-standard-public-zone-redundant-portal
6 | Configure Nat services for egress traffic | Simplifies egress IP management to external 3rd party applications and services |  |  |  |  | https://docs.microsoft.com/en-us/azure/virtual-network/nat-overview
7 | Delegate a Management subnet to host JumpHost VMs | Recommended for secure management of infrastructure within network
8 | Define compute requirements | Using business objectives, make decisions on what compute requirements we will need to leverage in cloud platform. |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/considerations/compute-options#identify-compute-services-requirements
9 | Define traffic management requirements for intra-region load balancing | Define configuration and rules for traffic management requirments. Deploy if this requirement is needed |  |  |  |  | https://docs.microsoft.com/en-us/azure/load-balancer/load-balancer-overview
10 | Define Traffic management for inter-region load balancing | Define configuration and rules for traffic management requirments. Deploy if this requirement is needed |  |  |  |  | https://docs.microsoft.com/en-us/azure/traffic-manager/traffic-manager-overview
11 | Define traffic management for Intra-region L7 HTTP WAF | Define configuration and rules for traffic management requirments. Deploy if this requirement is needed |  |  |  |  | https://docs.microsoft.com/en-us/azure/application-gateway/overview
12 | Define Traffic management for Inter-region L7 HTTP WAF | Define configuration and rules for traffic management requirments. Deploy if this requirement is needed |  |  |  |  | https://docs.microsoft.com/en-us/azure/frontdoor/front-door-overview

## Storage
Story: As a cloud enablement team, we need to define and deploy storage requirements into the cloud
Acceptance Criteria: Deploy storage solutions cross the various data platforms that support durable, scalable, and redunancy to meet your data requirements
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Review and define azure storage options needed to match project workloads | Leveraging the array of storage services, define which solutions match the requirements of workloads we intend moving or building on the platform. |  |  |  |  | https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/ready/considerations/storage-options#select-storage-tools-and-services-to-support-your-workloads
2 | Enable redunancy in your storage platform | Type of redundancy chosen should match both the pricing and SLA requirements for our data |  |  |  |  | https://docs.microsoft.com/en-us/azure/storage/common/storage-redundancy
3 | Enable the appropriate access & performance tiers | Optimize expense on storage by implementing both the appropriate access and performance teird to complement your data usage patterns |  |  |  |  | https://docs.microsoft.com/en-us/azure/storage/blobs/storage-blob-storage-tiers?tabs=azure-portal https://docs.microsoft.com/en-us/azure/storage/blobs/storage-blob-performance-tiers
4 | Review data migration options and implement the appropriate infrastructure/connectivity to support it | [5 empty] | https://docs.microsoft.com/en-us/azure/storage/common/storage-choose-data-transfer-solution?toc=/azure/storage/blobs/toc.json
5 | Enable Service endpoints to storage services to support network restirction to azure based private networks | Required for firewalled access to private azure virtual network only |  |  |  |  | https://docs.microsoft.com/en-us/azure/storage/common/storage-network-security?toc=/azure/virtual-network/toc.json#grant-access-from-a-virtual-network
6 | Enable Private endpoints to storage services to support network restriction to entire private hybrid network infrastructure | Required for firewalled access to private azure virtual networks and on-premise networks |  |  |  |  | https://docs.microsoft.com/en-us/azure/storage/common/storage-private-endpoints
7 | Design a recovery and account failover plan for our data | Important in order to stafisy RPO objectives |  |  |  |  | https://docs.microsoft.com/en-us/azure/storage/common/storage-disaster-recovery-guidance?toc=/azure/storage/blobs/toc.json

## Monitoring
Story: As a cloud enablement team, we need to implement a monitoring strategy to analyze, audit and alert on Hybrid cloud resources.
Acceptance Criteria: Implement a comprehensive solution for collecting, analyzing and acting on telemetry from cloud platform
Tasks
ID | Name | Description | Comments | Assigned to | Start Date | End Date | Artifacts & Documentation
1 | Enable Centralized workspace for collection of logs and metrics from platform resources | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-monitor/overview
2 | Enforce log and metric reporting to centralized work space across all resources on platform | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-monitor/insights/vminsights-enable-at-scale-policy
3 | Create customized dashboard views for real time analysis and issue tracking | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-monitor/visualizations
4 | Design and create alerts and actions based on critical condition scenarios | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-monitor/platform/alerts-overview
5 | Review partner integration scenarios for data integration with existing on-premise services | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-monitor/platform/partners
6 | Deploy and enforce network monitoring capabilities across hybrid network architecture | [5 empty] | https://docs.microsoft.com/en-us/azure/network-watcher/network-watcher-monitoring-overview
7 | Determine and deploy integration with exsiting ITSM solution | [5 empty] | https://docs.microsoft.com/en-us/azure/azure-monitor/platform/itsmc-connections
8 | Configure alerting for platform resource and service health events | [5 empty] | https://docs.microsoft.com/en-us/azure/service-health/alerts-activity-log-service-notifications https://docs.microsoft.com/en-us/azure/service-health/resource-health-alert-arm-template-guide